## Instructions
CHANGE TRACKER – INSTRUCTIONS
Purpose:
This tracker logs proposed and implemented changes affecting processes, documents, equipment, software, or other quality-impacting systems.
It supports traceability, cross-functional accountability, and closure tracking for both ISO and GMP environments.
How to Use:
1. Enter a unique Change ID and describe the change clearly.
2. Assign an Owner and responsible Function.
3. Select the Change Type, Reason, and Risk Level from dropdowns.
4. Update Status and QA Review fields throughout the lifecycle.
5. Use the Final Review Date when change is approved/closed.
6. Track updates in the Change Log for version control.
Dropdown values can be customized in the 'Dropdown Options' sheet.

## Change Tracker
Change ID | Date Submitted | Area Affected | Description of Change | Owner | Function | Type of Change | Reason for Change | Risk Level | Requires QA Review? | Status | Final Review Date | Notes
CHG-001 | 2025-06-01 | Lot Release SOP | Updated acceptance criteria for in-process hold time. | Tina Y. | QA | SOP | Audit Observation | Medium | Yes | Complete | 2025-06-10 | Reviewed and signed off by QA Manager.
CHG-002 | 2025-06-08 | MES System | Added version control for release step. | Mark S. | Manufacturing | Software | Process Improvement | High | Yes | In Progress |  | Pending validation approval.
CHG-003 | 2025-06-15 | Training Policy | Created policy for new hire onboarding within 5 days. | Helly R. | MSAT | Organizational | CAPA Follow-Up | Low | No | Open
CHG-004
CHG-005
CHG-006

## Dropdown Options
Change Types | Reasons | Functions
SOP | Audit Observation | QA
Equipment | Process Improvement | MSAT
Software | CAPA Follow-Up | Manufacturing
Organizational | NPI / Product Launch

## Change Log
Version | Change Description | Author | Date
v1 | Created Change Tracker with form-style layout, dropdown references, and example rows. | Josh Villanueva | 2025-06-23