## Project Overview
PROJECT OVERVIEW – GANTT TRACKER
Initiative Name | QMS Deployment – Phase 1-3 Rollout
Initiative Owner / Champion | Helly R.
Start Date | 2025-07-01
Target End Date | 2025-09-01
Overall Timeline Duration (Days) | 62
Context Notes | This tracker covers the staggered rollout of quality documentation, training, and audit readiness efforts across core QMS areas.

## Instructions
QUALITY SYSTEM PROJECT TRACKER – INSTRUCTIONS
WHAT THIS FILE TRACKS:
This tool is a Gantt-based project tracker designed to help cross-functional teams coordinate the phased implementation of quality system activities.
It includes:
- A live Gantt chart based on real task data
- Role-based assignments and color-coded rows by phase
- A milestone review sheet to log high-level deadlines or sign-offs
- Editable dropdowns and duration tracking
- Change history for auditability
SHEET-BY-SHEET GUIDE
1. PROJECT OVERVIEW
Enter your initiative name, owner/champion, target timeline, and key context notes.
This helps reviewers and cross-functional contributors understand the scope.
2. PROJECT TASKS
This is the main tracker table. Fill in:
- QMS Area (dropdown from 'Dropdown Options')
- Task name, Owner, Function
- Phase
- Start and End Dates (auto-calculates Duration)
- Status and Notes (as needed)
To add a new task: insert a new row within the table boundary. Excel will preserve formatting and formulas.
3. REVIEW DEADLINES
Use this sheet to log major review checkpoints or sign-off deadlines.
While these do not currently render as vertical lines on the Gantt, they serve as useful reference points for milestone planning.
4. GANTT CHART
This sheet contains a horizontal bar chart that automatically updates from the task table in 'Project Tasks'.
Bars represent duration (Start to End Date). Tasks are stacked vertically.
5. DROPDOWN OPTIONS
To customize the QMS Areas or Function dropdowns:
Edit the source lists in the 'Dropdown Options' sheet.
Changes will flow into the Project Tasks sheet automatically.
6. CHANGE LOG
Use this sheet to track versions and changes for team visibility or audit support.
TIPS:
- Use phases to group related tasks or workstreams.
- You can customize conditional formatting by Phase or Status.
- Keep task descriptions short and clear for clean Gantt visuals.

## Project Tasks
QMS Area | Task | Owner | Function | Phase | Start Date | End Date | Duration (Days) | Status | Notes
Document Control | Draft SOP Template | Mark S. | QA | Phase 1 | 2025-07-01 | 2025-07-05 | 4 | Complete
Training & Qualification | Define Training Matrix | Helly R. | MSAT | Phase 1 | 2025-07-03 | 2025-07-12 | 9 | In Progress
Deviation Management | Create Change Tracker | Dylan G. | Process Engineering | Phase 2 | 2025-07-10 | 2025-07-20 | 10 | Not Started
Document Control | Finalize SOP Version Log | Tina Y. | Quality Systems | Phase 2 | 2025-07-20 | 2025-07-25 | 5 | Not Started
Audit Program | Schedule Dry Run Audit | Sasha T. | QA | Phase 3 | 2025-07-15 | 2025-08-01 | 17 | Not Started
Training & Qualification | Distribute Training Matrix | Ivan N. | MSAT | Phase 3 | 2025-08-01 | 2025-08-10 | 9 | Not Started
Audit Program | Conduct Mock Audit | Camila R. | QA | Phase 4 | 2025-08-15 | 2025-08-20 | 5 | Not Started

## Review Deadlines
Deadline Name | Reviewer | Presenters | Deadline Date
Phase 1 Review |  |  | 2025-07-10
Phase 2 Sign-Off |  |  | 2025-07-25
Final QA Review |  |  | 2025-08-20

## Dropdown Options
QMS Areas | Functions
Document Control | QA
Training & Qualification | MSAT
Deviation Management | Process Engineering
Audit Program | Quality Systems
Change Management | Manufacturing
Risk Management | Validation

## Change Log
Version | Change Description | Author | Date
v1 | Created Project Tracker with Gantt, dropdowns, and sample tasks | Josh Villanueva | 2025-06-22